## Sample Schedule Excerpts
Sample TimeLine |  |  | Cornell Cup
The rule is it is assumed that if the "Dependent On" column is blank, the task is dependent on the completion of the previous task above at the same level. i.e. PS.8 requires that PS.7 and its associated subtasks have been completed
Notice that PS.10 is listed as being "Dependent On" PS.7.5. This means the PS.10 can begin immediately after PS.7.5 is completed and that PS.10 does not require PS.8 nor PS.9 to be completed before PS.10 can begin. If PS.10 did require PS.9 to be completed as well, PS.10's "Dependent On" column would read "PS.7.5, PS.9"
A dependency without a number, i.e. is just a milestone ID, means that the entire milestone must be completed
* Indicates this task can be the starting point for this milestone
Start Date | Completed Date | Due Date | Team Member | Time Actual (hrs) | Time Req (hrs) | Effort (1-7) | Dependent On | ID | Sub-ID#s |  |  | Milestone | Task | SubTask 1 | SubTask 2 | SubTask 3 | Deliverables
[7 empty] | * | RICCR |  |  |  | ReviewCornell Cup Rules |  |  |  |  | All team members have read all the rules and discussed them
[7 empty] | * | GAS |  |  |  | Gain Advisor Support |  |  |  |  | Faculty member commits to acting as an advisor for the team for the upcoming academic year
[9 empty] | 1 |  |  |  | ReviewCornell Cup Rules |  |  |  | Advisors have read all the rules and discussed them
[8 empty] | CPC |  |  |  | Create Project Concept
[7 empty] | *RICCR |  | 1 |  |  |  | Brainstorm Ideas |  |  |  | List of potential ideas for the Challenge, prioritized in terms of both exciting and risk
[9 empty] | 2 |  |  |  | Perform initial search for already existent versions of ideas & whether ideas are feasible |  |  |  | Refined list of potential ideas for the Challenge, prioritized in terms of both exciting and risk
[7 empty] | GAS |  | 3 |  |  |  | Review with Advisor for Idea Selection |  |  |  | Determine which idea to pursue further, and what would be a back-up idea should something come
[9 empty] | 4 |  |  |  | Register Team |  |  |  | Register team on theCornell Cup website
[8 empty] | PD |  |  |  | Challenge Definition
[7 empty] | *CPC |  | 1 |  |  |  | Research Other Solutions to Similar Challenges |  |  |  | Create a List of solutions to similar challenges with references where more information can be found; List pros and cons of each solution
[9 empty] | 2 |  |  |  | Determine Key Use Cases |  |  |  | Written description of the way we intend the solution device to be used; Create a Context Diagram for the device; List of use case behavioral diagrams (matrices) for the most important ones
[9 empty] | 3 |  |  |  | Determine Key Requirements |  |  |  | List of originating requirements for the solution device
[9 empty] | 4 |  |  |  | Review challenge definition with Advisor |  |  |  | Approval of Challenge Solution research, Context Diagram, Behavior Diagrams, Solution Description, and Originating Requirements
[10 empty] | 1 |  |  |  | Identify potential Faculty Reviewers |  |  | List of other faculty who have expertise in this area and might be willing to act as a reviewer for the team
[9 empty] | 5 |  |  |  | Complete Application Write-Up for Challenge Definition |  |  |  | Challenge Definition write up is complete and reviewed by all team members
[8 empty] | PS |  |  |  | Proposed Solution
[7 empty] | *PD |  | 1 |  |  |  | Determine solution concept
[10 empty] | 1 |  |  |  | Determine main subsystems for solution concept |  |  | List of main subsystems for the proposed solution
[10 empty] | 2 |  |  |  | List initial feasibility issues & resource needs |  |  | List of potential feasibility issues and concern level in terms of at least uncertainty, time, and resource usage; Potential start of a FMEA matrix
[10 empty] | 3 |  |  |  | Address feasibility issues & resource needs |  |  | Written description of solution, Updated Use Cases & Requirements
[7 empty] | PD.1 |  | 2 |  |  |  | Functional Flow Diagram & Subsystems
[10 empty] | 1 |  |  |  | Create Functional Flow Diagram for Subsystem Connections |  |  | Functional Flow Diagram focusing on the inputs and outputs from each subsystem. New requirements for subsystem interfaces
[7 empty] | PD.1.2, CC.1 |  |  | 2 |  |  |  | Revisit initial feasibility issues & resource needs |  |  | Update list of potential feasibility issues and concern level in terms of at least uncertainty, time, and resource usage
[7 empty] | PD.2.1, PD.1.3 |  |  | 3 |  |  |  | Address new feasibility issues & resource needs |  |  | Update Functional Flow Diagram, Use Cases, & Requirements.
[7 empty] | PM.2 |  | 3 |  |  |  | Determine Potential Equipment Needed |  |  |  | List of at least Expensive / Hard to Obtain Equipment Anticipated
[7 empty] | PM.3 |  | 4 |  |  |  | Check for & Reserve Equipment Availability |  |  |  | Compare List with known lab equipment, Prepare questions for meeting with Advisor
[9 empty] | 5 |  |  |  | Contact Potential Reviewing Faculty |  |  |  | All identified Potential Reviewers contacted with role expectations and to see if there is initial interest Meetings set up with interested reviewers for just after main Advisor meeting
[9 empty] | 6 |  |  |  | Preparation for Review with Advisor |  |  |  | Updated Written description of Solution sent to advisor 48 hrs prior to meeting time, Update Functional Flow Diagram, Use Cases, & Requirements and be ready to discuss
[9 empty] | 7 |  |  |  | Review concept with Advisor
[10 empty] | 1 |  |  |  | Ensure solution meets the challenge's needs |  |  | Approval or Noted Modifications for Functional Flow Diagrams, Subsystem Breakdowns, Written Descriptions, and all Uses Cases & Requirements
[10 empty] | 2 |  |  |  | Ensure identified feasibility issues and resource needs are addressed |  |  | Approval or Noted Modifications for Functional Flow Diagrams, Subsystem Breakdowns, Written Descriptions, and all Uses Cases & Requirements
[10 empty] | 3 |  |  |  | Identify any new feasibility issues and resource needs are addressed |  |  | Update list of potential feasibility issues and concern level in terms of at least uncertainty, time, and resource usage
[10 empty] | 4 |  |  |  | Ensure team has / will be able to gain skills needed to create this solution |  |  | Approval from Advisor
[10 empty] | 5 |  |  |  | Discuss potential Reviewers responses |  |  | Approval from Advisor
[9 empty] | 8 |  |  |  | Improve ideas and create Final Proposed Solution |  |  |  | All Noted Modifications from Advisor Meeting are addressed
[10 empty] | 1 |  |  |  | Final Advisor Check |  |  | Approval from Advisor
[9 empty] | 9 |  |  |  | First Draft of Application Write-Up for Challenge Definition
[7 empty] | PD.7.5 |  | 10 |  |  |  | Confirm Faculty Reviewers for Project |  |  |  | Commitment from faculty that they will act as reviewers, List of tentative dates that may work good for reviewer(s) throughout the semester
[8 empty] | PM |  |  |  | Performance Measures
[7 empty] | *PD.3, PS.1.1 |  | 1 |  |  |  | Determine what functions your proposed solution performs that directly address the challenge needs |  |  |  | Matrix of Challenge's Needs (Rows) and the Key Functionality of Solution (Columns), where the cells show how strongly the functionality and the need are related
[10 empty] | 1 |  |  |  | Determine questions you want answered that would show your solution is meeting (or not meeting) these needs well |  |  | List of questions that could answer whether a need is met
[10 empty] | 2 |  |  |  | Determine ways to could obtain / measure answers to those questions (i.e. to form metrics) |  |  | List of potential tests that could be used to measuring the key functionalities' performance with respect to various challenge needs ; For each test, a list of output(s) (metrics) should be created
[7 empty] | PS.2.1 |  | 2 |  |  |  | Determine what are the critical components of the proposed solution for meeting the challenge's needs |  |  |  | List of components that are critical to the key solution functionality identified earlier as being important to meeting the challenge need
[10 empty] | 1 |  |  |  | Determine metrics/tests to show these components are operating well for your solution's important functionality |  |  | List potential tests for at least the core components as they relate to the key functionalities
[7 empty] | PS.3 |  | 3 |  |  |  | Estimate what kind of test equipment, data, time, etc would be required |  |  |  | Test lists are updated to include potential special or harder to obtain materials or test equipment, or require a significant amount of time to perform
[10 empty] | 1 |  |  |  | Review this in terms of feasibility |  |  | Refine test lists to make sure they are do-able within the time and resources available
[9 empty] | 4 |  |  |  | Review the Performance Measures and the Resources needed to collect them with your Advisor |  |  |  | Approval or Noted Modifications for Performance Metrics, Tests and Test Equipment/Resources
[10 empty] | 1 |  |  |  | Make any changes necessary |  |  | All Noted Modifications from Advisor Meeting are addressed
[10 empty] | 2 |  |  |  | Final Advisor Check |  |  | Approval from Advisor
[9 empty] | 5 |  |  |  | First Draft of Application Write-Up for Performance Measures
[8 empty] | TLM |  |  |  | TimeLine & Milestone Formation
[7 empty] | *PS.7 |  | 1 |  |  |  | Determine Key Milestones by examining, subsystems, key functionality, & testing for the proposed solution & performance metrics |  |  |  | List of Potential Milestones
[10 empty] | 1 |  |  |  | Determine what the main deliverables for each milestone will be |  |  | List of Expected outputs (deliverables) from each milestone
[9 empty] | 2 |  |  |  | Determine main tasks & subtasks to achieve each milestone's deliverables |  |  |  | List of tasks and subtasks for each milestone
[10 empty] | 1 |  |  |  | Split up Milestone's deliverables amongst tasks & subtasks where appropriate |  |  | Refer to parent task
[10 empty] | 2 |  |  |  | Add new deliverables to tasks & subtasks as needed |  |  | Refer to parent task
[10 empty] | 3 |  |  |  | Include testing tasks |  |  | Testing tasks added to milestones
[10 empty] | 4 |  |  |  | Include time for ordering parts |  |  | Ordering tasks added to milestones
[10 empty] | 5 |  |  |  | Include tasks for re-iteration |  |  | Review / Re-iteration tasks added to milestones
[9 empty] | 3 |  |  |  | Estimate the effort for task & subtask |  |  |  | Rank of 1-7 as to anticipated effort required for each task
[9 empty] | 4 |  |  |  | Estimate the correspondence between effort and time |  |  |  | Assigned an estimated hours to complete for each task; Leave as an equation so dates can be easily adjusted as the team gains experience in estimating their ability to perform various tasks
[9 empty] | 5 |  |  |  | Determine Dependencies between Tasks |  |  |  | List of tasks (if any) that need to be performed before each task
[9 empty] | 6 |  |  |  | Determine good times for Review Meetings |  |  |  | List of tentative times from advisor and review faculty that milestones
[9 empty] | 7 |  |  |  | Create Schedule of Tasks |  |  |  | Schedule is determined; Spreadsheet will work but Gantt or PERT charts might be preferable; Note which steps (most likely those later in the process) that have the most uncertainty in their time estimates
[10 empty] | 1 |  |  |  | Using dependencies, identify all potential starting tasks |  |  | List of potential starting tasks
[10 empty] | 2 |  |  |  | Identify critical path |  |  | Identify which sequence of tasks has to happen as soon as possible in order to have entire project end as soon as possible
[10 empty] | 3 |  |  |  | Using dependencies, determine which starting points or other tasks have significant slack in them |  |  | Recorded the slack for each task
[7 empty] | PD.10 |  | 8 |  |  |  | Check against course, exams, & advisor schedules |  |  |  | Adjusted schedule to be realistic to "outside of project" time demands
[8 empty] | CC |  |  |  | Concerns Check
[7 empty] | *PD.2.1 |  | 1 |  |  |  | Determine which parts of the solution would have the greatest impact and/or have the most uncertainty surrounding them |  |  |  | Assigned an impact/importance rating & an uncertainty rating to at least the tasks with the greatest effort, most dependencies, and/or are most critical to key solution functionality
[10 empty] | 1 |  |  |  | Modify solution to mitigate risks |  |  | Adjusted Functional Flow Diagram, Uses Cases, & Requirements to take into account considered risks
[11 empty] | 1 |  |  |  | Add requirements to mitigate risks |  | Added Requirements needed to address the identified uncertainties and reduce risk
[10 empty] | 2 |  |  |  | Determine Back-up plans for areas of greatest concern/uncertainty |  |  | List options for what could confidently be done instead should risks be realized
[10 empty] | 3 |  |  |  | Update Importance & Uncertainty ratings to account for the existence of back-up plans |  |  | Updated impact/importance ratings & an uncertainty ratings to at least the tasks with the greatest effort, most dependencies, and/or are most critical to key solution functionality
[7 empty] | TLM.7 |  | 2 |  |  |  | Re-Examine the proposed schedule for the effect of these potential uncertainties |  |  |  | Identified points in schedule where uncertainty would be answered or risk would be lessened once passed; Identified tasks where uncertainty / risk would have the greatest effect
[10 empty] | 1 |  |  |  | Examine schedule for worst case scenarios |  |  | Version of schedule where every activity takes the maximum expected time
[9 empty] | 3 |  |  |  | Re-Examine the proposed schedule for potential bottlenecks |  |  |  | Adjusted schedule that minimizes bottlenecks and offers suggested alternative work that can be done at potential bottleneck points
[7 empty] | PS.7 |  | 4 |  |  |  | Modify Proposed Solution that will be promised in the application to ensure that you can deliver what you promise |  |  |  | Adjusted Functional Flow Diagram, Uses Cases, Requirements, & Written solution description
[10 empty] | 1 |  |  |  | Sketch out back-up plan schedule for most critical/uncertain elements |  |  | Estimate on effort for all Back-up ideas
[10 empty] | 2 |  |  |  | Rank ideas that would like to be added to solution if time / resources allow |  |  | List of potential ideas ranked by estimates on benefit toward the challenge needs and effort to complete
[8 empty] | FFC |  |  |  | Final Feasibility Check
[7 empty] | *PS, CC, PM, |  | 1 |  |  |  | Review the proposed solution for feasibility |  |  |  | Teammates review sections that they were not the primary author of
[10 empty] | 1 |  |  |  | Make any changes necessary |  |  | Adjusted Functional Flow Diagram, Uses Cases, Requirements, & Written solution description as needed; Prepared questions for advisor
[7 empty] | FFC.1, TLM |  | 2 |  |  |  | Review the schedule for feasibility issues, leaving "extra" time for significant new challenges |  |  |  | Teammates review sections that they were not the primary author of
[10 empty] | 1 |  |  |  | Make any changes necessary |  |  | Adjusted Functional Flow Diagram, Uses Cases, Requirements, & Written solution description as needed; Prepared questions for advisor
[9 empty] | 3 |  |  |  | Review for approval with Advisor |  |  |  | Advisor addressed all questions; Suggested changes given; Required Resources Confirmed
[10 empty] | 1 |  |  |  | Make any needed changes |  |  | Adjusted Functional Flow Diagram, Uses Cases, Requirements, & Written solution description as needed; Prepared questions for advisor
[9 empty] | 4 |  |  |  | First Draft of Application Write-Up for Feasibility & Resources Available
[8 empty] | RC |  |  |  | List any remaining concerns (Be honest!)
[7 empty] | *FFC.3 |  | 1 |  |  |  | Re-check for reasonable options to mitigate the risk |  |  |  | Adjusted deliverables from tasks ########## to ########
[9 empty] | 2 |  |  |  | Ensure there are back-up plans should the concerns be realized |  |  |  | Adjusted deliverables from tasks ########## to ########
[9 empty] | 3 |  |  |  | First Draft of Application Write-Up for Potential Concerns & Alternative Plans
[8 empty] | AWU |  |  |  | Complete Application Write-Up
[7 empty] | *PD |  | 1 |  |  |  | Challenge Definition |  |  |  | Written by at least one team member; Reviewed by at least one other
[7 empty] | AWU.1, FFC.1 |  | 2 |  |  |  | Proposed Solution |  |  |  | Written by at least one team member; Reviewed by at least one other
[9 empty] | 3 |  |  |  | Performance Measures |  |  |  | Written by at least one team member; Reviewed by at least one other
[7 empty] | AWU.2, FFC.2 |  | 4 |  |  |  | Timeline & Milestones |  |  |  | Written by at least one team member; Reviewed by at least one other
[9 empty] | 5 |  |  |  | Feasibility & Resources Available |  |  |  | Written by at least one team member; Reviewed by at least one other
[9 empty] | 6 |  |  |  | Potential Concerns & Alternative Plans |  |  |  | Written by at least one team member; Reviewed by at least one other
[8 empty] | RAA |  |  |  | Review Application with Advisor and Team Reviewer
[7 empty] | *AWU |  | 1 |  |  |  | Present Application Materials |  |  |  | Meeting scheduled & conducted; Review sheets completed by all attendees; List of changes needed recorded
[9 empty] | 2 |  |  |  | Make any needed changes |  |  |  | All changed sections also reviewed by another team member
[8 empty] | SA |  |  |  | Submit Application
[7 empty] | *RAA |  | 1 |  |  |  | Submit all materials on-line |  |  |  | Confirmation Email Received
[8 empty] | TTV |  |  |  | Obtain Identified Target Test Vehicles
[7 empty] | *PM.4 |  | 1 |  |  |  | Reconfirm use of Prof. Johnson's Cervelo P4 |  |  |  | Confirmation in writing with tentative available dates and time
[7 empty] | *PM.4 |  | 2 |  |  |  | Order Sanitov trike |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | *PM.4 |  | 3 |  |  |  | Purchase 10 Speed Lab Bike from used bike store |  |  |  | Receipts turned into Advisors, Bike secured in lab
[7 empty] | *PM.4 |  | 4 |  |  |  | Reconfirm use of Motor Scooter from colleagues/classmates |  |  |  | Confirmation in writing with tentative available dates and time
[7 empty] | *PM.4 |  | 5 |  |  |  | Reconfirm use of Prius from colleagues/classmates |  |  |  | Confirmation in writing with tentative available dates and time
[8 empty] | PTD |  |  |  | Research Performance Test Data
[7 empty] | *PM.4 |  | 1 |  |  |  | Determine City Test Trip |  |  |  | Mapped route of streets and elevations for the test trip
[10 empty] | 1 |  |  |  | Determine Demand along route |  |  | Log of the demand along the city test trip, capable of being adjusted for various rider & cargo weights
[7 empty] | *PM.4 |  | 2 |  |  |  | Determine Hilly Test Trip |  |  |  | Mapped route of streets and elevations for the test trip
[10 empty] | 1 |  |  |  | Determine Demand along route |  |  | Log of the demand along the hilly test trip, capable of being adjusted for various rider & cargo weights
[7 empty] | *PD |  | 3 |  |  |  | Determine Test Cargo Weights |  |  |  | List of cargo weights to be considered in the tests
[7 empty] | *PD |  | 4 |  |  |  | Determine Test Rider Weights |  |  |  | List of rider weights to be considered in the tests
[8 empty] | WRS |  |  |  | Design Wheel Rotation Sensor System
[7 empty] | *TTV.3 |  | 1 |  |  |  | Determine Wheel Rotations Sensor Requirements |  |  |  | List of Wheel Rotations Sensor Requirements, Decision Matrix created for evaluating COTS encoders (empty but evaluation criteria is established)
[9 empty] | 2 |  |  |  | Find COTS Encoder(s) that meets/exceeds sensor requirements |  |  |  | Completed Decision matrix for the encoders
[10 empty] | 1 |  |  |  | Determine Microcontroller Interface Requirements |  |  | List of requirements for each encoder to be connected to a microcontroller or similar input device
[9 empty] | 3 |  |  |  | Determine tests for Encoder |  |  |  | List of tests and expected outcomes for the encoder (probably a short list)
[7 empty] | WRS.2 |  | 4 |  |  |  | Determine tests for Microcontroller |  |  |  | List of tests and expected outcomes for the microcontroller with regards to at least the encoder's needs (probably a short list)
[9 empty] | 5 |  |  |  | Determine tests for combined Microcontroller & Encoder |  |  |  | List of tests and expected outcomes for the encoder connected to the microcontroller (probably a short list)
[7 empty] | WRS.2 |  | 6 |  |  |  | Purchase Encoder |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WRS.2 |  | 7 |  |  |  | Purchase Microcontroller Interface Board (if needed) |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WRS.5 |  | 8 |  |  |  | Purchase any additional test components |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WRS.1 |  | 9 |  |  |  | Begin design of IR based encoder |  |  |  | Conceptual wiring diagram
[7 empty] | WRS.8 |  | 10 |  |  |  | Test Encoder |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 11 |  |  |  | Test Encoder with Microcontroller Interface Board |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[7 empty] | WRS.11, SA10B.1 |  | 12 |  |  |  | Attach Encoder to Test 10 Speed Bike |  |  |  | Developed and constructed sensor attachment mechanism. Encoder attached to bike and wired to microcontroller
[9 empty] | 13 |  |  |  | Test Encoder & Microcontroller on Bike to Reconfirm Sensor Requirements |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 14 |  |  |  | Re-examine wheel rotation sensor system as means for obtaining demand |  |  |  | Decision to continue or investigate back-up plans; If continue: Adjusted list of requirements for IR encoder sensor
[9 empty] | 15 |  |  |  | Documentation on COTS encoder selection & implementation |  |  |  | Written report including test data and conclusions
[7 empty] | WRS.14 |  | 16 |  |  |  | Modify & Complete IR based encoder design |  |  |  | Wiring diagram, parts selection
[10 empty] | 1 |  |  |  | Re-Examine the IR encoder design for potential ways the solution could fail |  |  | List of failure modes and potential sources & effects (FMEA); If we couldn't find any ways our design process could fail, we haven't been thorough enough
[10 empty] | 2 |  |  |  | Adjust design to account for identified failure modes |  |  | Updated wiring diagram, parts selection; Updated FMEA
[9 empty] | 17 |  |  |  | Determine tests for IR based encoder |  |  |  | List of tests and expected outcomes for the IR encoder
[9 empty] | 18 |  |  |  | Order Components for IR encoder & testing |  |  |  | Purchase order placed, Receipts turned into Advisors
[9 empty] | 19 |  |  |  | Build IR based encoder |  |  |  | Completed IR encoder with connections for microcontroller and other test equipment
[7 empty] | WRS.19, SA10B.2 |  | 20 |  |  |  | Test IR based encoder |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs ; Created Improvement Plans
[9 empty] | 21 |  |  |  | Review Results with Advisor |  |  |  | Present results & questions; Adjust designs/plans as decided; Go ahead to begin corrective actions (if any)
[9 empty] | 22 |  |  |  | Improve Sensor & Sensor Attachment Mechanism (if needed) |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 23 |  |  |  | Documentation for IR based encoder |  |  |  | Written report including construction guide, test data, and conclusions
[8 empty] | WFS |  |  |  | Design Wheel Force Sensor System
[7 empty] | *TTV.3 |  | 1 |  |  |  | Determine Wheel Force Sensor Requirements |  |  |  | List of Wheel Force Sensor Requirements, Decision Matrix created for evaluating COTS sensors (empty but evaluation criteria is established)
[9 empty] | 2 |  |  |  | Find COTS Wheels Sensors that meets/exceeds sensor requirements |  |  |  | Completed Decision matrix for the force sensors
[9 empty] | 3 |  |  |  | Determine Microcontroller Interface Requirements |  |  |  | List of requirements for each force sensor to be connected to a microcontroller or similar input device
[7 empty] | WFS.2 |  | 4 |  |  |  | Determine tests for Wheel Force Sensor |  |  |  | List of tests and expected outcomes for the force sensor (probably a short list)
[7 empty] | WFS.3 |  | 5 |  |  |  | Determine tests for Microcontroller |  |  |  | List of tests and expected outcomes for the microcontroller with regards to at least the force sensor's needs (probably a short list)
[9 empty] | 6 |  |  |  | Determine tests for combined Microcontroller & Wheel Force Sensor |  |  |  | List of tests and expected outcomes for the force sensor connected to the microcontroller (probably a short list)
[7 empty] | WFS.2 |  | 7 |  |  |  | Purchase Wheel Force Sensor |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WFS.3 |  | 8 |  |  |  | Purchase Microcontroller Interface Board (if needed) |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WFS.6 |  | 9 |  |  |  | Purchase any additional test components |  |  |  | Purchase order placed, Receipts turned into Advisors
[7 empty] | WFS.7 |  | 10 |  |  |  | Test Wheel Force Sensor |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 11 |  |  |  | Test Wheel Force Sensor with Microcontroller Interface Board |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[7 empty] | WFS.12, SA10B.3 |  | 12 |  |  |  | Attach Wheel Force Sensor to Test 10 Speed Bike |  |  |  | Developed and constructed sensor attachment mechanism. Force sensor attached to bike and wired to microcontroller
[9 empty] | 13 |  |  |  | Test Wheel Force Sensor & Microcontroller on Bike to Reconfirm Sensor Requirements |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs ; Created Improvement Plans
[9 empty] | 14 |  |  |  | Improve Sensor Placement (if needed) |  |  |  | Report on the variability and accuracy of the sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 15 |  |  |  | Re-examine wheel force sensor system as means for obtaining demand |  |  |  | Decision to continue or investigate back-up plans
[9 empty] | 16 |  |  |  | Review Results with Advisor |  |  |  | Present results & questions; Adjust designs/plans as decided; Go ahead to begin corrective actions (if any)
[10 empty] | 1 |  |  |  | Carry out decided changes |  |  | All desired changes made (check for new dependencies from new tasks created for making these changes)
[9 empty] | 17 |  |  |  | Documentation for Wheel Force Sensor |  |  |  | Written report including assembly guide, test data, and conclusions
[8 empty] | DSF |  |  |  | Design Sensor Filter
[7 empty] | *PD.8 |  | 1 |  |  |  | Begin work on the software components of the filter |  |  |  | Create standard Kalman filter framework such that filters only requires changing parameters in order to be implemented as real filter; List of parameters needed to complete software filter
[7 empty] | *WRS.20 |  | 2 |  |  |  | Examine IR sensor data for filter needs |  |  |  | List of noise issues with data as compared to data requirements; List of concepts to potentially improve data quality
[9 empty] | 3 |  |  |  | Design IR sensor hardware filter |  |  |  | Wiring diagrams and components list for at least one complete hardware solution approach. More approaches if there is uncertainty
[9 empty] | 4 |  |  |  | Order IR sensor filter hardware components |  |  |  | Purchase order placed, Receipts turned into Advisors
[9 empty] | 5 |  |  |  | Build IR sensor filter |  |  |  | Completed IR encoder filter with connections for microcontroller and other test equipment
[9 empty] | 6 |  |  |  | Test IR sensor filter |  |  |  | Report on the variability and accuracy of the filtered sensor; Decision as to whether the sensor will be adequate for the system's needs; Parameters needed for Software component of the flyer
[7 empty] | DSF.1, DSF.6 |  | 7 |  |  |  | Complete software filter for IR sensor |  |  |  | Bug-free software filter; expected output from contrived input for all anticipated use cases
[10 empty] | 1 |  |  |  | Internal Documentation for software sensor filter |  |  | All code classes, methods, and fields documented
[9 empty] | 8 |  |  |  | Test combined hardware & software filters |  |  |  | Report on the variability and accuracy of the filtered sensor; Decision as to whether the sensor will be adequate for the system's needs
[7 empty] | *WFS.10 |  | 9 |  |  |  | Examine wheel force sensor data for filter needs |  |  |  | List of noise issues with data as compared to data requirements; List of concepts to potentially improve data quality
[9 empty] | 10 |  |  |  | Design wheel force sensor hardware filter |  |  |  | Wiring diagrams and components list for at least one complete hardware solution approach. More approaches if there is uncertainty
[9 empty] | 11 |  |  |  | Order wheel force sensor filter hardware components |  |  |  | Purchase order placed, Receipts turned into Advisors
[9 empty] | 12 |  |  |  | Build wheel force sensor filter |  |  |  | Completed IR encoder filter with connections for microcontroller and other test equipment
[9 empty] | 13 |  |  |  | Test wheel force sensor filter |  |  |  | Report on the variability and accuracy of the filtered sensor; Decision as to whether the sensor will be adequate for the system's needs; Parameters needed for Software component of the flyer
[7 empty] | DSF.1, DSF.13 |  | 14 |  |  |  | Complete software filter for wheel force sensor |  |  |  | Bug-free software filter; expected output from contrived input for all anticipated use cases
[9 empty] | 15 |  |  |  | Test combined hardware & software filters |  |  |  | Report on the variability and accuracy of the filtered sensor; Decision as to whether the sensor will be adequate for the system's needs
[9 empty] | 16 |  |  |  | Improve Filters (if needed)
[9 empty] | 17 |  |  |  | Re-examine wheel force sensor system as means for obtaining demand |  |  |  | Decision to continue or investigate back-up plans
[9 empty] | 18 |  |  |  | Review Results with Advisor |  |  |  | Present results & questions; Adjust designs/plans as decided; Go ahead to begin corrective actions (if any)
[7 empty] | DSF.18 |  | 19 |  |  |  | Documentation for software sensor filter |  |  |  | Written report including pseudo-code, UML diagrams, test data, and conclusions
[7 empty] | DSF.18 |  | 20 |  |  |  | Documentation for hardware sensor filter |  |  |  | Written report including assembly guide, test data, and conclusions
[8 empty] | DDA |  |  |  | Design Demand Algorithm
[7 empty] | *PD.8 |  | 1 |  |  |  | Define core use cases for the algorithm |  |  |  | List of all possible inputs and respective desired outputs, define passing requirements for the algorithm to be considered fully functional
[7 empty] | *DSF.1 |  | 2 |  |  |  | Define kinds of data expected from sensors |  |  |  | A list of the data that is required for the sensor filter system to deliver to this algorithm
[7 empty] | DDA.1 |  | 3 |  |  |  | List any requirements for the algorithm construction |  |  |  | List of memory and runtime requirements, anticipated scale of the challenge, and legacy & library code required
[9 empty] | 4 |  |  |  | Create Pseudo-Code for core algorithm |  |  |  | Design algorithm pseudo-code for the most common / typical case to build intuition
[10 empty] | 1 |  |  |  | Review for other use cases that could exist |  |  | List all uses cases for the code, anticipating potential variations in input
[7 empty] | DDA.4, PTD.1, PTD.2 |  | 5 |  |  |  | Adjust Pseudo-Code to handle all identified use cases |  |  |  | Design algorithm pseudo-code to handle all identified use cases
[9 empty] | 6 |  |  |  | Determine Architecture & Data Structures |  |  |  | A list of the data structures that will represent the data from the sensor filter system and the data this algorithm needs to deliver to this algorithm
[7 empty] | DDA.2, DDA.6 |  | 7 |  |  |  | Create test data for algorithm |  |  |  | List of test data expected from sensors, including data sets that accurately represent any possible variations
[10 empty] | 1 |  |  |  | Select representative subset for basic testing |  |  | A sample of test data from each expected use case to be used in testing
[7 empty] | DDA.6 |  | 8 |  |  |  | Program Data Structures and General Architecture |  |  |  | Compiled code that meets all of the previously determined data structures and architecture requirements (List of requirements "checked-off')
[10 empty] | 1 |  |  |  | Internal Documentation |  |  | All code classes, methods, and fields documented
[9 empty] | 9 |  |  |  | Program algorithm |  |  |  | Produces expected demand results from provided test data to within algorithm requirements.
[10 empty] | 1 |  |  |  | Internal Documentation |  |  | All code classes, methods, and fields documented
[9 empty] | 10 |  |  |  | Program algorithm test code |  |  |  | Program is able to accept test data and report on result and performance accurately;
[10 empty] | 1 |  |  |  | Internal Documentation |  |  | All code classes, methods, and fields documented
[9 empty] | 11 |  |  |  | Perform basic testing |  |  |  | Code runs correctly for all standard use cases, bug free
[9 empty] | 12 |  |  |  | Perform test code testing |  |  |  | Produces expected output from provided test data; Report on the variability and accuracy of the entire sensor system; Decision as to whether the entire sensor system will be adequate for the system's needs
[9 empty] | 13 |  |  |  | Improve Implementation of Algorithm (if needed)
[7 empty] | DSF.18 |  | 14 |  |  |  | Update test data based upon real data from developed sensor system |  |  |  | Final test data set
[9 empty] | 15 |  |  |  | Determine final metrics |  |  |  | Update passing requirements
[9 empty] | 16 |  |  |  | Conduct algorithm testing via test code & test data |  |  |  | Program is able to accept test data and report on result and performance accurately; Report on the variability and accuracy of the entire sensor system; Decision as to whether the entire sensor system will be adequate for the system's needs
[9 empty] | 17 |  |  |  | Review Results with Advisor |  |  |  | Present results & questions; Adjust designs/plans as decided; Go ahead to begin corrective actions (if any)
[9 empty] | 18 |  |  |  | Documentation for software sensor filter |  |  |  | Written report including pseudo-code, UML diagrams, test data, and conclusions
[8 empty] | SA10B |  |  |  | Design Sensor Attachments for 10 Speed bike testing
[7 empty] | *WRS.6 |  | 1 |  |  |  | Determine Encoder mounting requirements |  |  |  | List of sensor mounting requirements
[7 empty] | WRS.19 |  | 2 |  |  |  | Determine IR Encoder mounting requirements |  |  |  | List of sensor mounting requirements
[7 empty] | *WFS.7 |  | 3 |  |  |  | Determine Wheel Force Sensor mounting requirements
[7 empty] | SA10B.1 |  | 4 |  |  |  | Design Encoder Attachment Mechanisms
[9 empty] | 5 |  |  |  | Order Encoder Attachment Mechanisms Parts
[9 empty] | 6 |  |  |  | Build Encoder Attachment Mechanisms
[7 empty] | SA10B.2 |  | 7 |  |  |  | Design IR Encoder Attachment Mechanisms
[9 empty] | 8 |  |  |  | Order IR Encoder Attachment Mechanisms Parts
[9 empty] | 9 |  |  |  | Build IR Encoder Attachment Mechanisms
[7 empty] | SA10B.3 |  | 10 |  |  |  | Design Wheel Force Sensor Attachment Mechanisms |  |  |  | CAD drawings, machining and assembly guide, parts list
[9 empty] | 11 |  |  |  | Order Wheel Force Sensor Attachment Mechanisms Parts |  |  |  | Purchase order placed, Receipts turned into Advisors
[9 empty] | 12 |  |  |  | Build Wheel Force Sensor Attachment Mechanisms |  |  |  | Assembled attachment mechanisms; List of tests and pass conditions created
[7 empty] | WRS.23 |  | 13 |  |  |  | Update Encoder Sensors' documentation |  |  |  | Written report addition including attachment mechanism construction and assembly guide
[7 empty] | WFS.17 |  | 14 |  |  |  | Update Wheel Force Sensors' documentation |  |  |  | Written report addition including attachment mechanism construction and assembly guide
[8 empty] | CSS_SF |  |  |  | Combine Sensor Suite with Sensor Filter
[7 empty] | *DSF.16, WRS.22, WFS.17 |  | 1 |  |  |  | Determine test requirements for successful combination test |  |  |  | List of success criteria
[9 empty] | 2 |  |  |  | Determine test plan for combination |  |  |  | Test plans that can potentially produce success criteria
[9 empty] | 3 |  |  |  | Conduct combination test |  |  |  | Actual resulting criteria from test
[9 empty] | 4 |  |  |  | Analyze results |  |  |  | Checklist of successful and unsuccessful test criteria; List of potential reasons for failures
[9 empty] | 5 |  |  |  | Plan corrective actions |  |  |  | Updated new task list with new deliverables
[9 empty] | 6 |  |  |  | Review results with Advisor |  |  |  | Present results & questions; Adjust plans as decided; Go ahead to begin corrective actions (if any)
[9 empty] | 7 |  |  |  | Update Sensor Suite and Sensor Filter Documentation |  |  |  | Written report addition including testing protocols for interfaces, assembly instructions, and test results
[8 empty] | CSF_DA |  |  |  | Combine Sensor Filter with Demand Algorithm
[7 empty] | *DDA.11, DSF.16 |  | 1 |  |  |  | Determine test requirements for successful combination test |  |  |  | List of success criteria
[9 empty] | 2 |  |  |  | Determine test plan for combination |  |  |  | Test plans that can potentially produce success criteria
[9 empty] | 3 |  |  |  | Conduct combination test |  |  |  | Actual resulting criteria from test
[9 empty] | 4 |  |  |  | Analyze results |  |  |  | Checklist of successful and unsuccessful test criteria; List of potential reasons for failures
[9 empty] | 5 |  |  |  | Plan corrective actions |  |  |  | Updated new task list with new deliverables
[9 empty] | 6 |  |  |  | Review results with Advisor |  |  |  | Present results & questions; Adjust plans as decided; Go ahead to begin corrective actions (if any)
[9 empty] | 7 |  |  |  | Update Sensor Suite and Sensor Filter Documentation |  |  |  | Written report addition including testing protocols for interfaces, assembly instructions, and test results
[8 empty] | CSS_SF_DA |  |  |  | Combine Sensor Suite, Sensor Filter, & Demand Algorithm
[7 empty] | *CSS_SF.5, CSS_DA.5 |  | 1 |  |  |  | Determine test requirements for successful combination test |  |  |  | List of success criteria
[9 empty] | 2 |  |  |  | Determine test plan for combination |  |  |  | Test plans that can potentially produce success criteria
[9 empty] | 3 |  |  |  | Conduct combination test |  |  |  | Actual resulting criteria from test
[9 empty] | 4 |  |  |  | Analyze results |  |  |  | Checklist of successful and unsuccessful test criteria; List of potential reasons for failures
[9 empty] | 5 |  |  |  | Plan corrective actions |  |  |  | Updated new task list with new deliverables
[9 empty] | 6 |  |  |  | Review results with Advisor |  |  |  | Present results & questions; Adjust plans as decided; Go ahead to begin corrective actions (if any)
[9 empty] | 7 |  |  |  | Update Sensor Suite and Sensor Filter Documentation |  |  |  | Written report addition including testing protocols for interfaces, assembly instructions, and test results
MILESTONES are defined typically by an achievement of functionality or as a group of related tasks that require a similar skill set
Note on K20: : Read as "PD.4.1"

## Dave's Guidelines
Don't Panic. The purpopse of making these lists is to create for your team an easy step by step task list so you can check your overall and individual progress and to help identify problems/setbacks/bottlenecks early on so they can be dealt with early
Please feel free to copy paste and modify this list for the creation of your own task list
List tasks
Review the task list to see if there are any key subtasks you should list out
Review the task list to make sure you've included time for testing your designs, for ordering parts, documentation, and review of your progress with your advisor(s)
Sometimes even though you may feel a subtask is implied within a task, listing out a task can be a good way to make sure its not forgotten or will be addressed seriously at a certain point in the schedule, particularly if you expect someone else will be carrying out the tasks you are creating
Normally it can take a few passes through the entire task list before you can feel confident that your task list is fairly complete.
Take a break
Add deliverable column
Review task list & deliverables in light of the deliverables
Identify dependencies of tasks, particularly between subtasks belonging to different main tasks
Begin to create a schedule based upon dependencies, showing only the required order not indicating the effort or time of the task
If you find that two tasks, task A and task B, depend upon each other (cyclically, i.e. like the chicken & the egg), split at least one of the tasks into 2, let's say A1 and A2, such that the first half of A, A1, delivers the part of A that B needs and then task B delivers to task A2 what task A originally needed from B. This may sometime take the form that task A1 is to estimate certain parameters that B needs and then task A2 is to finalize those parameters based upon the results of task B.
Add Effort column
If a task requires significantly more effort than others, split it into smaller tasks
This could take several days (its usually best to ask each person on the team to create part of it and then in combining the parts, teammates are able to review each others work and look for important dependncies. Often this helps team members recognize what their teammates will be expecting from them and a way for team members to say what they're expecting from their teammates
Record Time it takes for future planning reference
At this phase of your overall deisgn prorcess some of the deliverables may not be very detailed as you need information from preceeding tasks in order to fill in those details. This is expected and acceptable particularly at this design phase
Deliverables that are depended on by other subtasks, particularly other subtasks that are part of different milestones, are usually the ones that should be spelled out in the most detail
Not all Milestones are the same length, or have similar effort levels. They represent a key aspect of the project with a clear start and ending point. Often a milestone is also defined in terms a defined subset of required skills
A good example is within the Design Demand Algorithm. The algorithm needs to know as much information as possible about its incoming filtered sesnor data, however the Design Sensor Filter needs to know how "well filtered" the data needs to be for the algorithm to run.
Example of a Discussion between 2 Team Members where one has agreed to take on programming the demand algorithm and the other has agreed to take on the design demand algorithm
Each team member has discovered in developing their task list that they need information (aka a deliverable) from the other for a key part of their work. Unfortunately it appeatrs that
Programming Team Member | Well I know the algorithm is expecting to take this kind of information
Filter Developing Team Member | Well I know the sensor data often needs a high pass filter but
Okay let me take a look at what I've read about these algorithms you can
I found out that there is a parameter you can adjust as to how much variance you're expecting and the algorithm will be able to compensate. However there is a limit and the reference I found says it can really vary from case to case. so I'm just not sure how much variance the system can handle
Chances are most of the time you will experience something in between these two. Watch yourself for phrases similar to those in the first example. If they start to occur this is a good warning sign that you should re-examine your planning. Focus on what you CAN do with what you have at moment, not what can't do, and think about what can be done to help you progress toward your goals.
Beware of Feature Creep
Its common that in development of one feature, the opportunity to create new features or improve upon an existing feature may arise
This can be potentially great and/or crippling. When these new ideas arise. First step jot it down. Regardless of whether you pursue it now or not get the idea recorded in some fashion
Then treat the idea as a small milestone and determine the tasks, subtasks, . It may feel like it takes a little wind out of your sails to formalize the idea, but that loss of wind is more often due to the realization of just how much extra effort the new ideas will take
This is far better than venturing headstrong down a certain path and then realize midstream that the end is far more complicated than you realized. Often the initial feeling of "This is so cool! I just gotta do this to make it happen" leads to another "well I just gotta do this now and then it will be done" which can lead to a "well its taking a bit longer than expected but once its done it will be great" and the to "well it will take me at least one more week but then I can go back to those other things I was working on". This is often the core of the feature creep problem and how exploring new ideas that initially seem very exciting may take away from other project aspects that need to get done and instead the new idea would be better addressed later on in the project or perhaps left out entirely until perhaps the next iteration of the entire project
Bottlenecks
Unexpected bottlenecks can occur and may be outside of your control. A late part, a piece of equipment breaks, or unexpected results or additional assignments can cause a part of the project to lag.
In cases like these reexamine the schedule to see if other aspects can be worked on in parallel
Also look for how you can do everything you can possibly do such that when that deliverable is available (i.e. the part finally came in) you are instantly ready to make use of that deliveriable. (i.e. all of the supporting wiring and physical attachment for that part has already been made, we just need to plug that part in and we can begin testing)
Later in the timeline steps may not be as detailed and deliverables may become more generic. It is CRITICAL, that throughout the implementation of the time line that these tasks and deliverables be updated with more specific measureable information
Please recognize that you are welcome to start the development of your entry during the application time period. i.e. you do not need to be accepted to being your project if your advisor approves
Recorded Time it takes for future planning reference